# Diners Club Japan (www.diners.co.jp)

# Adobe Edge Delivery Services (EDS) Migration Analysis

Date: June 2026
Source URL: https://www.diners.co.jp/
Total pages analyzed (from sitemap): 1765
Operator: Sumitomo Mitsui Trust Club Co., Ltd.
Source platform: Adobe Experience Manager (AEM Sites)

# Table of Contents

1. Executive Summary

2. Templates Inventory

3. Blocks / Components Catalog

4. Page Counts by Template & Migration Approach

5. Integrations Analysis

6. Migration Estimates

7. Assumptions & Notes

# 1. Executive Summary

www.diners.co.jp is the consumer website for Diners Club Japan, operated by Sumitomo Mitsui Trust Club Co., Ltd. (SMTC). It is built on Adobe Experience Manager (AEM Sites) using a mix of WCM Core Components (cmp-*) and bespoke custom components (CCM### family), with the global header and footer delivered as Experience Fragments shared with its sister site www.sumitclub.jp.

The live sitemap exposes 1,765 published pages. The content is dominated by three high-volume, highly-templated families: the editorial "Magazine" (601 article pages), "Benefit / Merchant" detail pages (470), and dated "Press / News" articles (258). These standardized families are excellent candidates for automated bulk import into EDS, which is why ~91% of the estate is auto-migratable.

The migration is low-to-medium risk overall. The main complexity is not page volume but the surrounding integrations — site search, the Club Online member system, the Helpfeel FAQ, the external card-application forms, and heavy ad/analytics tagging — all of which are external systems that should be re-pointed rather than rebuilt.

| Metric | Value |
| --- | --- |
| Total pages (sitemap) | 1765 |
| Unique page templates | 10 |
| Reusable blocks / components | 24 |
| Auto-migratable pages | ≈ 1,610 (91%) |
| Manual / assisted pages | ≈ 155 (9%) |
| Estimated total effort | ≈ 92–110 person-days |
| Estimated schedule | ≈ 13–15 weeks (3–3.5 months) |

# 2. Templates Inventory

Nine unique page templates were identified across the 1,765 pages. Templates are grouped by structural layout and content pattern rather than by URL folder, so a single template typically spans many sections of the site.

| Template | Complexity | Reasoning | Reference URLs |
| --- | --- | --- | --- |
| Homepage | High | Hero carousel (CCM020), audience-segment navigation grid, "Important notices" ribbon, dual news feeds (お知らせ / ご確認ください), promo tiles. One-off layout. | https://www.diners.co.jp/ja/index.html |
| Article (Magazine) | Low | Standardized editorial article: breadcrumb, title, hero image, rich-text body, inline images, related-article list, category tags. Highly repetitive (601 pages). | https://www.diners.co.jp/ja/magazine/article/shopping/watch_jewelry/tiffany.html |
| Benefit / Merchant detail | Medium | Bespoke template: image gallery, benefit-summary tables, store-info table, map/access text, CTA. Consistent structure but data-dense (470 pages). | https://www.diners.co.jp/ja/benefit/detail.R1882.html |
| Article / News detail | Low | Dated press-release / event-report article: date, category, title, rich text, attachments. Very standardized (258 pages). | https://www.diners.co.jp/ja/press/inf_20260601.html https://www.diners.co.jp/ja/event/report/e00160.html |
| Category / Service / How-to | Medium | Core-Component pages (travel, gourmet, golf, usage, point, payment, insurance, corporate, merchant): page heading, side sub-nav (CCM027), image+text, step blocks, accordion, CTA, tables. Layout varies per section (374 pages). | https://www.diners.co.jp/ja/travel/hotel.html https://www.diners.co.jp/ja/usage/applepay.html |
| Product / Card detail | Medium | Card-spec layout: hero card image, feature grid, fee/benefit tables, comparison, apply CTA to external entry form (43 pages). | https://www.diners.co.jp/ja/cardlineup/dinersclubcard.html |
| Listing / Index | Medium | Section landing/listing pages with filters, card grids and load-more news lists (magazine library, press index, benefit index, card lineup). | https://www.diners.co.jp/ja/magazine/library.html https://www.diners.co.jp/ja/press.html |
| Legal / Policy text | Low | Long-form text: headings, paragraphs, tables, link lists. Privacy, terms, small print, customer-response policy (13 pages). | https://www.diners.co.jp/ja/privacy.html https://www.diners.co.jp/ja/tc.html |
| Contact / Support | Medium | Accordion of inquiry types + gateway buttons that launch external form widget / Helpfeel FAQ / phone directory (1 hub page). | https://www.diners.co.jp/ja/contact.html |
| Sitemap | Low | Single hierarchical link-list page. | https://www.diners.co.jp/ja/sitemap.html |

Note: header and footer are AEM Experience Fragments shared with www.sumitclub.jp and contain cross-domain links and Adobe Experience Cloud (adobe_mc) ID-sync parameters. These should become a single EDS nav/footer block, and the cross-domain parameters can be dropped on EDS.

# 3. Blocks / Components Catalog

The following 24 reusable blocks were identified across the site. Per the brief, visually different layouts that share the same content model are captured as "variants" of one block rather than as new blocks (e.g. card grid vs. news list).

| Block / Component | Variants | Complexity | Description & Behaviour |
| --- | --- | --- | --- |
| Global Header / Nav | 1 | High | Logo, utility links (Club Online, lost-card, search), site search box, corporate-site link, primary nav. Experience Fragment shared with sumitclub.jp. |
| Global Footer | 1 | Medium | Brand/partner logos, Remote Operator link, corporate link, copyright. Experience Fragment. |
| Breadcrumb | 1 | Low | Hierarchical path navigation (CCM013). |
| Side / Secondary Nav | 1 | Low | In-section sub-navigation menu (CCM027). |
| Hero / Page Heading | 2 | Low | Page title with optional background/hero image. Variant: card-image hero on product pages. |
| Carousel / Banner | 1 | Medium | Auto-advancing banner slider with prev/next + dots (CCM020 / slick). |
| Card Grid / Listing | 3 | Medium | Grid of linked cards (image+title+text). Variants: benefit grid, magazine grid, product/card lineup grid. |
| News / Press List | 2 | Medium | Dated list with category badge + title + "load more". Variants: homepage feed, full press/notice index. |
| Related Items List | 1 | Low | Related-article / related-card list at page foot. |
| Rich Text | 1 | Low | Body copy with headings, lists, links (CCM006). |
| Raw HTML Embed | 1 | Medium | Arbitrary embedded HTML/markup block (CCM005). |
| Data Table | 2 | Low | Fee/benefit/spec tables. Variants: spec table, comparison table. |
| Accordion / Toggle | 1 | Low | Expand/collapse FAQ or content sections. |
| Tabs | 1 | Medium | Tabbed content switcher. |
| Image + Text | 2 | Low | Media-and-copy block. Variants: image-left, image-right. |
| Step / Process Block | 1 | Low | Numbered how-to / step sequence. |
| CTA Button | 2 | Low | Primary call-to-action (CCM009). Variants: internal link, external/apply link. |
| Link List | 2 | Low | Grouped lists of links (CCM008). Variants: inline list, sitemap tree. |
| Image Gallery / Thumbnails | 1 | Medium | Thumbnail gallery on benefit/merchant pages. |
| Social Share | 1 | Low | Share buttons (JS window.open) on articles. |
| Notice / Ribbon | 1 | Low | Highlighted important-notice strip. |
| Category Tag / Badge | 1 | Low | Article category labels. |
| Video Embed | 1 | Medium | YouTube embeds (brand movie, articles). |
| Search Box | 1 | Medium | Header site-search form (GET to search.diners.co.jp). External search engine. |

## 3.1 Reconciliation with Team-Identified Block List

The team's Excel block/integration sheet (Sheet1 = blocks, Sheet2 = integrations) was not available to this analysis at the time of writing. The table below lists the blocks identified from the live site so they can be diffed against the team list. Please confirm the "vs. Team List" column; items marked "Confirm" are additions or consolidations this analysis recommends.

| Recommendation | Block(s) | Rationale |
| --- | --- | --- |
| Consolidate as variants | Card Grid (benefit / magazine / product); News List (homepage / index); Image+Text (left / right); Hero (standard / card) | Same content model, different visual layout — build one block with variants instead of separate blocks, reducing block count and dev effort. |
| Confirm / likely additions | Raw HTML Embed (CCM005), Side/Secondary Nav (CCM027), Step/Process block, Image Gallery, Notice ribbon, Social Share | Present on the live site; verify these exist in the team list, as they are easy to overlook but affect parser scope. |
| Treat as integration, not block | Search Box, Login/Club Online button, FAQ launcher | These are gateways to external systems; scope them in the Integrations section, not as content blocks. |

# 4. Page Counts by Template & Migration Approach

Page counts below are derived by classifying all 1,765 sitemap URLs into the nine templates from Section 2.

| Template | Pages | % of site | Migration approach | Rationale |
| --- | --- | --- | --- | --- |
| Article (Magazine) | 601 | 34.1% | Automated | Uniform article structure; bulk import with spot-check QA. |
| Benefit / Merchant detail | 470 | 26.6% | Assisted | Consistent template but data-dense tables/galleries; bulk import + per-page review. |
| Category / Service / How-to | 374 | 21.2% | Assisted | Core-Component pages with per-section layout variation; bulk import + cleanup. |
| Article / News detail | 258 | 14.6% | Automated | Highly standardized dated press/event articles. |
| Product / Card detail | 43 | 2.4% | Manual | Marketing-critical card pages; rebuild for pixel-fidelity + external apply CTA. |
| Legal / Policy text | 13 | 0.7% | Automated | Plain long-form text + tables. |
| Listing / Index | 4 | 0.2% | Manual | Filtering / load-more behaviour needs an EDS index + query. |
| Contact / Support | 1 | 0.1% | Manual | External form widget + FAQ launcher wiring. |
| Sitemap | 1 | 0.1% | Automated | Single link-list page. |
| TOTAL | 1,765 | 100% | — | — |

Migration approach key — "Automated": pages with standardized structure that the import pipeline (block parsers + page transformers) can convert in bulk with spot-check QA. "Assisted": bulk-imported but require per-page review/cleanup. "Manual": custom layout, dynamic/system-driven, or external-integration pages that must be rebuilt or re-pointed by hand.

# 5. Integrations Analysis

The site embeds several third-party / external systems. Most should be re-pointed or re-embedded in EDS rather than reimplemented.

| Integration | Purpose | Migration handling |
| --- | --- | --- |
| Site Search (search.diners.co.jp) | On-site search | Re-point header search form, or replace with EDS/Edge search. |
| Club Online (sumitclub.jp/JPCRD) | Member login / self-service | External system — link out; out of EDS scope. |
| Helpfeel | FAQ / help knowledge base | External — keep as outbound link / embed. |
| Card application forms (entry_form/lp) | New-card applications | External landing pages — link out. |
| External inquiry form widget | General contact form | JS-injected widget — re-embed or replace with EDS form. |
| YouTube | Brand / article video | Re-embed via EDS video block. |
| e-book / library viewer | Magazine digital viewer | External viewer — link/embed. |
| Adobe Analytics / Target + adobe_mc | Analytics & personalization, cross-domain ID | Re-tag via EDS; drop cross-domain params. |
| Meta Pixel / Logly / ad trackers | Advertising & remarketing | Re-add required tags only; many can be retired. |
| Remote Operator (sumitclub.rmop.jp) | Co-browse support | External — link out. |

# 6. Migration Estimates

Estimates assume an automated EDS import pipeline (block parsers + page transformers) is built once and reused across all standardized templates, with a blended rate and a small migration team (2–3 engineers + 1 QA). Page volume is high but highly repetitive, so per-page cost is low for the article/news families.

## 6.1 Effort by Work-stream

| Work-stream | Effort (person-days) | Notes |
| --- | --- | --- |
| Discovery & template design | 6–8 | Confirm templates, design EDS block models. |
| Block development (24 blocks, with variants) | 22–26 | Build + style blocks; shared header/footer; variant consolidation reduces count. |
| Import pipeline (parsers + transformers) | 12–15 | Per-template parsers for magazine, benefit, press/event, category, product. |
| Automated content migration (≈1,610 pages) | 10–14 | Bulk runs + reruns; mostly compute, light human time. |
| Manual / assisted pages (≈155 pages) | 14–18 | Card pages, listings, contact, benefit/category cleanup. |
| Integrations re-wiring | 8–10 | Search, forms, video, analytics, login links. |
| QA & Testing | 14–16 | Visual QA, link checks, responsive, cross-browser. |
| PM / coordination / UAT support | 6–8 | Across the engagement. |
| TOTAL | 92–110 | ≈ 13–15 weeks elapsed with a 2–3 person team. |

## 6.2 Content Migration Effort by Template

| Template | Pages | Approach | Effort |
| --- | --- | --- | --- |
| Article (Magazine) | 601 | Automated | 3–4 days (bulk + QA sampling) |
| Benefit / Merchant detail | 470 | Assisted | 6–8 days (import + review) |
| Category / Service / How-to | 374 | Assisted | 5–6 days (import + cleanup) |
| Article / News detail | 258 | Automated | 1.5–2 days |
| Product / Card detail | 43 | Manual | 5–6 days (high fidelity) |
| Legal / Policy text | 13 | Automated | 0.5 day |
| Listing / Index | 4 | Manual | 2–3 days (index + query) |
| Contact / Support | 1 | Manual | 1–2 days (form wiring) |
| Sitemap | 1 | Automated | 0.25 day |

## 6.3 Timeline / Schedule

| Phase | Duration | Key outputs |
| --- | --- | --- |
| Phase 1 — Discovery & design | Weeks 1–2 | Template catalog, block models, pipeline design. |
| Phase 2 — Block & pipeline build | Weeks 3–6 | All blocks + import parsers/transformers ready. |
| Phase 3 — Bulk migration | Weeks 6–9 | Automated import of ~1,610 standardized pages. |
| Phase 4 — Manual pages & integrations | Weeks 9–12 | Card pages, listings, contact, integrations. |
| Phase 5 — QA, UAT & launch | Weeks 12–15 | Visual QA, fixes, go-live. |

## 6.4 Cost Summary

| Scenario | Effort (person-days) | Indicative range* |
| --- | --- | --- |
| Low (optimistic) | 92 | 92 × blended day-rate |
| High (conservative) | 110 | 110 × blended day-rate |

*Cost is expressed in person-days; apply your blended daily rate to convert to currency. As an illustration, at a representative offshore/near-shore blended rate of USD 500–700/day, the engagement falls roughly in the USD 46k–77k range. Replace with your contracted rate for a firm number.

# 7. Assumptions & Notes

Page counts are taken from the live sitemap (https://www.diners.co.jp/ja/Sitemap.xml) on the analysis date; 1,765 published pages, single Japanese locale.

Header and footer are shared Experience Fragments with www.sumitclub.jp; building them once can be amortized if both sites are migrated together.

External systems (Club Online member portal, Helpfeel FAQ, card-application forms, site search) remain on their current platforms and are linked/embedded, not rebuilt.

Ad-tech and analytics tags are rationalized during migration; only business-required tags are re-added.

The team's Excel block/integration list was not available at writing time; Section 3.1 should be reconciled against it before finalizing scope.

Estimates assume a 2–3 engineer + 1 QA team and reuse of the EDS import accelerator tooling; they exclude content rewriting, new design, translation, and post-launch support.