Adobe Experience Manager → Edge Delivery Services

Migration Discovery & Analysis Report

Diners Club Japan  •  TRUST CLUB (Sumitomo Mitsui Trust Club)

www.diners.co.jp  |  www.sumitclub.jp

Prepared for: Migration Planning Team

Date: 16 June 2026

# Executive Summary

This report consolidates the discovery findings for two related properties — diners.co.jp (Diners Club Japan) and sumitclub.jp (TRUST CLUB) — and translates them into a structured migration plan for Adobe Edge Delivery Services (EDS / Document-based authoring).

Both sites are sister properties operated by Sumitomo Mitsui Trust Club and are currently built on the same classic Adobe Experience Manager (AEM 6.x) platform. This is a material finding: they share one common component library (the "CCM" component set), one header/footer/navigation system, AEM Core Components (cmp-*), and near-identical page-construction patterns. The two sites therefore behave as a single migration program with a shared block library, not two independent projects.

Key facts at a glance

| Metric | Diners Club (diners.co.jp) | TRUST CLUB (sumitclub.jp) | Combined |
| --- | --- | --- | --- |
| Total published pages (sitemap) | 1,765 | 439 | 2,204 |
| Page template (AEM) | diners-club_ | trust-club_ | 2 variants, 1 base |
| Underlying platform | AEM 6.x (classic) | AEM 6.x (classic) | Shared instance |
| Distinct content templates | 8 | 8 | 8 (shared model) |
| Blocks (team discovery / EDS target) | 53 / 35 | 53 / 35 (shared) | 35 EDS blocks |
| Auto-migratable share (est.) | ~88% | ~85% | ~87% |
| Languages | Japanese (+EN sub) | Japanese + English | JA primary |

Headline estimate: the combined program is estimated at approximately 103–133 working days of effort (≈ 4.5–6 calendar months with a small dedicated team), with roughly 87% of pages eligible for automated, parser-driven migration and the remainder requiring manual / assisted handling (application flows, member-only "Club Online" areas, iframe-embedded forms, and heavily designed campaign landing pages).

Note on the supplied spreadsheet: Section 2 is built on the team’s "Post Discovery – Analysis.xlsx" Sheet 1 (53 blocks), reproduced in full (2.1) and then reconciled against the live sites and consolidated to 35 EDS blocks (2.2–2.3). Sheet 2 (integrations) was not visible in the supplied screenshot; the integrations catalogue (2.4) is assembled from the block-list notes plus live observation — please confirm it against Sheet 2 to close any gaps.

# 1. Templates Inventory

Although both sites technically render through a single AEM page template (diners-club_ / trust-club_) built on a flexible parsys/responsive-grid, the content falls into eight recurring authoring patterns. For migration planning these patterns are the meaningful "templates": they determine the parser logic and the EDS section model. Complexity reflects layout variability, dynamic behaviour, and embedded integrations — not page count.

## 1.1  Diners Club (diners.co.jp)

| Template | Complexity | Reasoning | Reference URLs |
| --- | --- | --- | --- |
| T1 — Homepage / Section Landing | High | Hero carousel (slick), audience navigation, "important notices" feed, news list, promo grids. Many distinct blocks; mostly one-off layout. | https://www.diners.co.jp/ja/index.html https://www.diners.co.jp/ja/travel.html https://www.diners.co.jp/ja/gourmet.html |
| T2 — Card Detail / Product Page | High | Long-form product page: card-spec tables, fee tables, comparison sliders, FAQ, embedded application CTAs and iframes. Richest component mix on the site. | https://www.diners.co.jp/ja/cardlineup/dinersclubcard.html https://www.diners.co.jp/ja/cardlineup/anadiners_new.html |
| T3 — Card Lineup / Comparison | Medium | Filterable card grid, dropdown filters, comparison tables, tabs. Standardised but interactive. | https://www.diners.co.jp/ja/cardlineup.html https://www.diners.co.jp/ja/cardlineup/comparison.html |
| T4 — Benefit / Service Detail | Medium | Standardised content body: intro, image+text blocks, link lists, accordions. 473 pages, very consistent structure → high auto-migration. | https://www.diners.co.jp/ja/benefit.html https://www.diners.co.jp/ja/benefit/stock.html |
| T5 — Magazine / Editorial Article | Medium | Editorial layout: rich text, full-width imagery, pull quotes, related-article cards, occasional video. 603 pages — the largest single group. | https://www.diners.co.jp/ja/magazine.html https://www.diners.co.jp/ja/magazine/library.html |
| T6 — Press / Notice Article | Low | Dated text article: title, date, body copy, occasional table/PDF link. Highly uniform → ideal for automated migration. | https://www.diners.co.jp/ja/press.html https://www.diners.co.jp/ja/press/inf_20260601.html |
| T7 — Legal / Policy / Info | Low | Plain rich-text: terms, privacy, prospectus. Tables but no interactivity. Fully auto-migratable. | https://www.diners.co.jp/ja/privacy.html https://www.diners.co.jp/ja/tc.html |
| T8 — Sitemap / Index | Low | Auto-style link directory. One page; trivial to rebuild. | https://www.diners.co.jp/ja/sitemap.html |
| T9 — Application / Form / Member (special) | High | Card application ("nyukai"), contact, 3-D Secure registration, "Club Online" member area. Forms are iframe-embedded external systems → out of CMS scope; landing wrappers migrate, the flows do not. | https://www.diners.co.jp/ja/cardlineup/nyukai.html https://www.diners.co.jp/ja/contact.html https://www.diners.co.jp/ja/usage/3d_secure/new_registration.html |

## 1.2  TRUST CLUB (sumitclub.jp)

TRUST CLUB uses the same eight patterns (same component library and header/footer), so the template definitions above apply directly. The notable site-specific groups are below.

| Template | Complexity | Reasoning | Reference URLs |
| --- | --- | --- | --- |
| T1 — Homepage / Section Landing | High | Hero, recommended-cards grid, service & support grid, notices, FAQ promo. Same block family as Diners. | https://www.sumitclub.jp/ja/index.html https://www.sumitclub.jp/ja/travel.html |
| T2 — Card Detail / Product | High | Card spec, fee tables, benefits, application CTA. Mirrors Diners T2. | https://www.sumitclub.jp/ja/cardlineup/world.html https://www.sumitclub.jp/ja/cardlineup/platinummaster.html |
| T4 — Benefit / Service Detail | Medium | Travel / gourmet / point / insurance service pages. Consistent structure. | https://www.sumitclub.jp/ja/travel/airport/airportlounge.html https://www.sumitclub.jp/ja/insurance/buyers.html |
| T6 — Notice Article | Low | Dated notices (104 pages) — uniform, fully auto-migratable. | https://www.sumitclub.jp/ja/notice/inf_20260601.html |
| T7 — Legal / Policy | Low | Terms, privacy, prospectus, anti-social-forces policy. | https://www.sumitclub.jp/ja/privacy.html https://www.sumitclub.jp/ja/tc.html |
| T9 — Member / Login / Application (special) | High | "loginPage" tree (41 pages) and Club Online member area — iframe / external application system. Public wrappers migrate; secured flows are out of scope. | https://www.sumitclub.jp/ja/cardlineup/nyukai.html https://www.sumitclub.jp/ja/loginPage.html |
| T10 — Corporate Site (sub-site) | Medium | Separate /corporate tree (company info, news, sustainability) with EN mirror. ~87 pages; standard editorial/landing mix. | https://www.sumitclub.jp/ja/corporate_site.html https://www.sumitclub.jp/corporate/kaizen/2204.html |

# 2. Blocks / Components Catalog

This section takes the team’s discovery catalogue from "Post Discovery – Analysis.xlsx" (Sheet 1 — 53 blocks) as the baseline, reproduces it faithfully (2.1), then applies the guidance to prefer design variations over net-new blocks and reconciles it against the live sites (2.2). The result is a leaner recommended EDS block library (2.3). Section 2.4 catalogues the third-party integrations.

## 2.1  Team discovery baseline (Sheet 1 — 53 blocks)

Reproduced from the supplied workbook. "C/C" = Core or Custom; "Var" = number of style variations identified; "SV" indicates whether the style variation was measured in the existing AEM library.

| # | Block | Diff. | C/C | Var | Linked feature / note |
| --- | --- | --- | --- | --- | --- |
| 1 | Text | Low | Core | 4 | Normal / Centered / Small. HTML editability TBC |
| 2 | Headings | Low | Core | 6 | H1–H4 / Centered / Thumbnail. Heading icon |
| 3 | Links | Low | Core | 3 | Normal / Inline / Phone number. Targeting |
| 4 | Lists | Low | Core | 4 | Normal / Normal(S) / Numbering. Auto-index |
| 5 | Lists Links Description | Low | Core | 1 | Link + description list. Not in library |
| 6 | Images | Low | Core | 7 | No style / centered / 100% etc. Benefit-detail gallery |
| 7 | Divider | Low | Core | 1 | Standard divider |
| 8 | Columns | Low-Med | Core | 6 | Grid / left-aligned grid. Important notices auto-index |
| 9 | Buttons | Low | Core | 8 | CTA(S/L) / normal. Card application / QSRF / KARTE / Targeting |
| 10 | Buttons Share | Low | Custom | 1 | SNS share button. Share-button JS |
| 11 | FAQ Details | Low | Core | 1 | Open-close (details) |
| 12 | Phrase | Low | Custom | 2 | A type / P type. COL phrase |
| 13 | Anker Navigation | Low | Custom | 1 | Anchor nav auto-generation JS |
| 14 | Icons | Low | Core | 1 | Icon set (fontello → standard) |
| 15 | Video | Low | Core | 1 | Standard video |
| 16 | Embed | Low | Core | 1 | YouTube embed |
| 17 | Hero | Low-Med | Core | 2 | MV slide (carousel 1-col) / SP segment. Dedicated Hero not in library |
| 18 | Accordion | Medium | Core | 2 | Default / exclusive open-close. cmp-accordion measured |
| 19 | Tabs | Medium | Core | 2 | Normal / SP accordion. Benefit-detail plan tabs / Auto-index |
| 20 | Table | Medium | Core | 2 | Standard / 2-col non-stacking on SP. HTML authoring TBC |
| 21 | Section Metadata | Medium | Core | 4 | Member-type & PC/SP segmentation. Partly in library |
| 22 | Cards | Medium | Custom | 3 | Manual edit / auto-index / JS+JSON. teaser measured |
| 23 | Cards Card Info | Medium | Custom | 2 | Campaign list / event list (CIX012). AES-autoi CSS only |
| 24 | Cards Benefit Step | Low | Core | 1 | Step layout (Cards variant). Named variant not in library |
| 25 | Cards Card Lineup | Low | Core | 1 | Card lineup (Cards variant) |
| 26 | Cards Magazine | Low | Core | 1 | Magazine (Cards variant) |
| 27 | Cards Privilege Icon | Low | Core | 1 | Privilege icon (Cards variant) |
| 28 | Cards Prize | Low | Core | 1 | Prize (Cards variant) |
| 29 | Cards Service Introduction | Low | Core | 1 | Service intro (Cards variant) |
| 30 | Carousel | Medium | Core | 3 | 1 / 3 / 4-col slide. AES-carousel measured |
| 31 | Fragment | Medium | Core | 3 | Individual / corporate / contact-common. Header segmentation |
| 32 | Footer | Medium | Core | 5 | Individual / corporate / travel / service. Menu handling |
| 33 | Header | High | Custom | 4 | DPC / RPC / general / corporate. Cookie detection, custom JS |
| 34 | Left Menu | Medium | Custom | 2 | PC menu / SP 2nd menu (JS). Indiv-corp segmentation |
| 35 | Breadcrumbs | Medium | Custom | 3 | Individual / corporate co-display / mid-category |
| 36 | Modal | Medium | Core | 1 | Standard modal. FAQ / Travel desk / Airport lounge |
| 37 | Page Style | Medium | Custom | 1 | Per-page custom style (~3 pages). MV segmentation |
| 38 | Sitemap | Medium | Custom | 2 | sitemap.xml (custom) / sitemap page. Auto-generation |
| 39 | Buttons FAQ | Medium | Custom | 1 | FAQ button (Helpfeel). May be unnecessary |
| 40 | Buttons Float | Medium | Custom | 1 | Floating button auto-display / QSRF Linker |
| 41 | Buttons Clipboard Copy | Medium | Custom | 1 | Copy button (Clipboard API) |
| 42 | Related Pages | Medium | Custom | 1 | Related-pages list. Current-page exclusion |
| 43 | Search | Medium | Custom | 1 | Site search (i-search) |
| 44 | Search Insite | Medium | Custom | 1 | Site search, card-type cookie variable (i-search) |
| 45 | Travel Desk | Medium | Custom | 2 | Recommended travel info / scrollbar. XML-driven |
| 46 | Embed Custom | Medium | Custom | 2 | HTML-only / HTML+CSS/JS. Receiver for packaged HTML + legacy |
| 47 | Benefit Detail | High | Custom | 4 | Gourmet / other / domestic / overseas. Shop JSON, member seg |
| 48 | Cards Campaign Event Benefit | High | Custom | 2 | Campaign/event (CIX012/013). query-index fetch, 2-system merge |
| 49 | Cards Event Report | High | Custom | 2 | Report list / top display. eventList.json fetch, JS+JSON sort |
| 50 | Lists Announcement | High | Custom | 2 | Year-based accordion / count flat. AES-list-notice measured |
| 51 | Google Maps | High | Custom | 1 | googleapis. JS API init, key/domain restriction, CSP |
| 52 | Airport Lounge Domestic | High | Custom | 1 | Domestic (CDN010). XML-driven |
| 53 | Airport Lounge International | High | Custom | 2 | airport-list / detail. DCI API + App Builder relay, CORS/auth |

## 2.2  Reconciliation against the live sites

Having inspected both live sites, the team’s catalogue is accurate and thorough — the live DOM confirms the AEM Core Components (cmp-*), the CCM/AES custom set, and the carousel/accordion/tab behaviours listed. Applying the "variants over new blocks" principle, several entries are structurally identical and should collapse into a single EDS block addressed by named variants. A small number of clarifications are added from the live findings.

| Action | Affected entries | Recommendation & rationale |
| --- | --- | --- |
| CONSOLIDATE | #22–29 (Cards + 6 "Cards X" variants) and #48, #49 | Single "Cards" block. The team already labels #24–29 as Cards variants; #23/#48/#49 are data-driven variants (auto-index / JSON fetch). Model as one block: variants = manual, auto-index, json. Net: 10 entries → 1 block (+ variants). Biggest single reduction. |
| CONSOLIDATE | #9, #10, #39, #40, #41 (Buttons family) | Single "Button" block with variants (cta, share, faq, float, copy). Share/FAQ/float/copy differ only by a small JS behaviour attached to the same model. Net: 5 → 1. |
| CONSOLIDATE | #43, #44 (Search, Search Insite) | One "Search" block; the card-type cookie is a config option, not a second block. Net: 2 → 1. |
| CONSOLIDATE | #16, #46 (Embed, Embed Custom) | One "Embed" block, variants = youtube, html, html+js. Net: 2 → 1. |
| CONSOLIDATE | #52, #53 (Airport Lounge Domestic / International) | One "Airport Lounge" block with domestic/international variants; both are API/XML-driven lists. Net: 2 → 1. (Still High effort — keep as integration.) |
| GROUP (chrome) | #31–35 (Fragment, Footer, Header, Left Menu, Breadcrumbs) | Treat as the shared navigation/chrome system, built once per brand and reused. In EDS these are nav + footer + fragments, not per-page content blocks. |
| MERGE | #5 into #4 (Lists) | "Lists Links Description" is a Lists variant (link + description). Net: 2 → 1. |
| CONFIRM (keep) | #47 Benefit Detail, #50 Lists Announcement, #51 Google Maps, #45 Travel Desk | Genuinely distinct High-complexity blocks (member-segmented shop data, year-grouped notices, Maps JS API, XML travel feed). Keep as first-class blocks. |
| NO ADDITIONS NEEDED | — | The live audit surfaced no block missing from the team’s list. Items I might otherwise add (notice feed, iframe form wrapper, card-spec) are already covered by #50, #46 and #47 respectively. |

## 2.3  Recommended consolidated EDS block library

After the reconciliation, the 53 discovery entries map to ≈ 30 EDS blocks (the difference being variants rather than separate blocks). This is the recommended build list.

| # | EDS Block | Effort | Replaces (Sheet 1 #) |
| --- | --- | --- | --- |
| 1 | Text | Low | 1 |
| 2 | Headings | Low | 2 |
| 3 | Links | Low | 3 |
| 4 | Lists | Low | 4, 5 |
| 5 | Images | Low | 6 |
| 6 | Divider | Low | 7 |
| 7 | Columns / Section layout | Low | 8 |
| 8 | Button | Low | 9, 10, 39, 40, 41 |
| 9 | FAQ / Details | Low | 11 |
| 10 | Phrase | Low | 12 |
| 11 | Anchor Navigation | Low | 13 |
| 12 | Icons | Low | 14 |
| 13 | Video | Low | 15 |
| 14 | Embed | Low | 16, 46 |
| 15 | Hero | Low-Med | 17 |
| 16 | Accordion | Medium | 18 |
| 17 | Tabs | Medium | 19 |
| 18 | Table | Medium | 20 |
| 19 | Section Metadata | Medium | 21 |
| 20 | Cards | Medium-High | 22–29, 48, 49 |
| 21 | Carousel | Medium | 30 |
| 22 | Header (chrome) | High | 33, 34 |
| 23 | Footer (chrome) | Medium | 32 |
| 24 | Fragment (chrome) | Medium | 31 |
| 25 | Breadcrumbs | Medium | 35 |
| 26 | Modal | Medium | 36 |
| 27 | Page Style | Medium | 37 |
| 28 | Sitemap | Medium | 38 |
| 29 | Related Pages | Medium | 42 |
| 30 | Search | Medium | 43, 44 |
| 31 | Travel Desk | Medium | 45 |
| 32 | Benefit Detail | High | 47 |
| 33 | Lists Announcement | High | 50 |
| 34 | Google Maps | High | 51 |
| 35 | Airport Lounge | High | 52, 53 |

Result: 53 discovery entries → 35 EDS blocks (≈ 34% fewer), with no loss of functionality. 14 Low, 13 Medium, 1 Low-Med / Medium-High, 7 High.

## 2.4  Integrations catalog

The supplied workbook lists integrations on Sheet 2 (not visible in the provided screenshot). The catalogue below is assembled from the integration notes embedded in the block list plus the third-party services observed loading on the live sites. Please confirm against Sheet 2 to close any gaps.

| Integration | Used by / where | Migration impact |
| --- | --- | --- |
| Adobe Analytics / DTM (Launch) | Sitewide tag (satelliteLib / adobedtm) | Re-add tag via EDS head/scripts. Low. |
| Adobe Experience Cloud ID (adobe_mc) | Cross-domain links diners ↔ sumitclub | Preserve cross-domain identity params. Low-Med. |
| Google Tag Manager | Sitewide | Re-add container. Low. |
| Meta (Facebook) Pixel | Sitewide marketing tag | Re-add. Low. |
| Logly / ad & DSP pixels (bidswitch, adnxs, ladsp) | Marketing/retargeting | Re-add tags; verify consent. Low. |
| Helpfeel (cards-faq-custhelp) | FAQ buttons (#39), "よくあるご質問" | External FAQ service; link/embed only. Low. |
| i-search | Site search (#43, #44) | Search service integration; re-wire query + cookie variant. Medium. |
| Google Maps JavaScript API (#51) | Store/location maps | API key, domain restriction, CSP entry. Medium-High. |
| DCI API + Adobe App Builder relay (#53) | Airport lounge international list | CORS/auth via App Builder; keep relay or re-point. High. |
| XML / JSON content feeds | Travel desk (#45), airport (#52), shop data (#47), query-index (#48), eventList.json (#49) | Re-create feeds or fetch logic in block JS. Medium-High per feed. |
| Club Online (WA2010101 / member system) | Header CTA, member area | External application; link out only — out of CMS scope. N/A. |
| Remote Operator (rmop.jp) | Footer support tool | External link. Low. |
| KARTE / on-site personalisation & Targeting | Buttons (#9), Links (#3) | Re-instrument personalisation tags. Medium. |
| QSRF Linker | Card application / float button (#40) | Application-flow linker; preserve params. Medium. |
| Clipboard API (#41) | Copy button | Native browser API; trivial. Low. |
| fontello icon set (#14) | Iconography | Migrate to standard icon sprite/SVG. Low. |

# 3. Page Counts by Template

Counts are derived from the live XML sitemaps (diners.co.jp = 1,765 URLs; sumitclub.jp = 352 main + 87 corporate = 439 URLs). Migration mode reflects structural uniformity: uniform, content-driven pages are parser-automatable; pages with bespoke layout, heavy interactivity or external integrations need manual / assisted work.

## 3.1  Diners Club (diners.co.jp) — 1,765 pages

| Template / Section | Pages | Migration Mode | Basis |
| --- | --- | --- | --- |
| T5 Magazine (editorial) | 603 | Automated | Uniform editorial structure |
| T4 Benefit / Service detail | 473 | Automated | Highly consistent body layout |
| T6 Press / Notice | 173 | Automated | Dated text articles |
| T1/T4 Event | 88 | Automated | Landing + detail, standard blocks |
| T1/T4 Travel | 77 | Automated | Service pages |
| T5 Lifestyle | 71 | Automated | Editorial |
| T2/T3 Card Lineup & Detail | 44 | Manual / Assisted | Tables, comparison, application CTAs |
| T1/T10 Corporate | 44 | Automated | Standard content |
| T4 Merchant | 39 | Automated | Service/info pages |
| T9 Usage / Guides | 31 | Mixed | 3DS & registration = manual; rest auto |
| T4 Point / Gourmet / Golf | 39 | Automated | Service detail |
| T9 Campaign (cpn_evt) | 15 | Manual / Assisted | Bespoke LP styling |
| T4 Shopping/Finance/Insurance/Kameiten/Payment | 36 | Automated | Service detail |
| T7 Legal / Policy / About / Sponsorship | 21 | Automated | Plain rich text |
| T1 Homepage + misc | 11 | Manual / Assisted | Bespoke homepage layout |

Diners split: ≈ 1,556 automated (88%) · ≈ 209 manual / assisted (12%).

## 3.2  TRUST CLUB (sumitclub.jp) — 439 pages

| Template / Section | Pages | Migration Mode | Basis |
| --- | --- | --- | --- |
| T6 Notice | 104 | Automated | Dated text articles |
| T9 Login / Member area | 41 | Manual / Out-of-scope | iframe / external auth system |
| T4 Travel | 63 | Automated | Service detail |
| T9/T4 Usage / Guides | 46 | Mixed | Some external links/forms |
| T2/T3 Card Lineup & Detail | 21 | Manual / Assisted | Spec/fee tables, application |
| T4 Point | 15 | Automated | Service detail |
| T4 Insurance | 12 | Automated | Service detail |
| T7 Legal / Policy | 12 | Automated | Plain rich text |
| T1/T4 Entertainment | 7 | Automated | Service detail |
| T9 Campaign | 5 | Manual / Assisted | Bespoke LP |
| T9 Contact | 3 | Manual | iframe form wrappers |
| T1 Home + Gourmet + misc | 23 | Mixed | Homepage bespoke; rest auto |
| T10 Corporate sub-site (ja+en) | 87 | Automated | Standard editorial/landing |

TRUST CLUB split: ≈ 373 automated (85%) · ≈ 66 manual / assisted / out-of-scope (15%).

## 3.3  Combined totals

| Migration Mode | Diners | TRUST CLUB | Combined | Share |
| --- | --- | --- | --- | --- |
| Automated (parser-driven) | 1,556 | 373 | 1,929 | ~87% |
| Manual / Assisted | 209 | 66 | 275 | ~13% |
| Total | 1,765 | 439 | 2,204 | 100% |

# 4. Migration Estimates

Estimates assume the EDS Document-based authoring model with a bulk import pipeline (block parsers + page transformers), a shared block library reused across both brands, and one combined program. Effort is expressed in person-days (1 day = 8h). Ranges reflect low / high confidence.

## 4.1  Effort breakdown

| Work Stream | Description | Effort (days) |
| --- | --- | --- |
| Discovery & setup (done/finalise) | Template confirmation, block inventory reconciliation, EDS project scaffold, import infra. | 6 – 8 |
| Block library development | 35 EDS blocks (14 Low, 13 Medium, 7 High incl. Benefit Detail, Lists Announcement, Google Maps, Airport Lounge), variants, CSS/JS. Reused across both brands. | 30 – 38 |
| Parser / transformer development | Per-template parsers (8 patterns) + cleanup/section transformers. | 10 – 13 |
| Automated content migration | ~1,929 pages via bulk import, batched by template, with spot-fixing. | 12 – 16 |
| Manual / assisted migration | ~275 pages: card detail/spec, campaigns, homepages, iframe-form wrappers, member-area landings. | 20 – 26 |
| Navigation, header & footer instrumentation | Desktop + mobile + mega-menu per brand; footer link columns. | 5 – 7 |
| QA & testing | Visual regression, link/redirect checks, responsive + accessibility, content parity sampling. | 12 – 15 |
| Project management & UAT support | Coordination, stakeholder reviews, go-live support. | 8 – 10 |

Total estimated effort: ≈ 103 – 133 person-days (midpoint ≈ 118 days).

## 4.2  Indicative schedule

| Phase | Calendar duration | Parallelism |
| --- | --- | --- |
| Phase 0 — Setup & reconciliation | Weeks 1–2 | Lead + 1 dev |
| Phase 1 — Blocks + parsers (both brands) | Weeks 2–7 | 2 devs |
| Phase 2 — Automated bulk migration | Weeks 6–10 | 1 dev + 1 author |
| Phase 3 — Manual / assisted pages | Weeks 8–14 | 1–2 authors/devs |
| Phase 4 — Nav/header/footer + integrations | Weeks 9–13 | 1 dev |
| Phase 5 — QA, UAT & go-live | Weeks 13–18 | Full team + QA |

Overall timeline: ≈ 4.5 – 6 calendar months with a 2–3 person core team (some phases overlap).

## 4.3  Indicative cost

Cost uses a blended rate placeholder; replace with the contracted day-rate to finalise. Calculation: midpoint effort 118 days.

| Blended day-rate (placeholder) | Low (103 d) | Midpoint (118 d) | High (133 d) |
| --- | --- | --- | --- |
| $800 / day | $82,400 | $94,400 | $106,400 |
| $1,000 / day | $103,000 | $118,000 | $133,000 |
| $1,200 / day | $123,600 | $141,600 | $159,600 |

## 4.4  Key assumptions & risks

- Both sites share one component library and chrome — block development is done once and reused, which is the single biggest efficiency in this estimate.

- Content freeze (or delta-handling plan) is in place during bulk migration; the 2,204 figure is the current sitemap snapshot and will drift.

- Forms (contact, card application, 3-D Secure) and the "Club Online" member area are external/iframe systems and are OUT of content-migration scope — only their wrapper pages migrate. Re-platforming these is a separate workstream if required.

- Japanese-language content (and the TRUST CLUB English mirror) imports cleanly; font/typography parity verified in QA.

- Estimates exclude net-new design, brand redesign, SEO redirect-map sign-off beyond standard 1:1 mapping, and third-party integration rebuilds (search, analytics tags, ad pixels).

- PDFs and DAM assets are migrated by reference / bulk asset copy, not re-authored.

End of report — figures are planning estimates and should be confirmed against the reconciled discovery spreadsheet and contracted rates.